# STRATEGIC PLAN

2026-2030

# BULINGA TECHNICAL SECONDARY SCHOOL

#### Building Excellence in ICT and Business Education

Location: Kiyoro Vilage, Munazi Cell, Mushishiro Sector, Muhanga District, Southern Province, Rwanda

Date: February 2026

Table of Contents

BULINGA TECHNICAL SECONDARY SCHOOL	1

EXECUTIVE SUMMARY	4

Key Strategic Priorities	4

Expected Outcomes by 2030	5

Resource Requirements	5

SECTION 1: INTRODUCTION & BACKGROUND	5

About Bulinga TSS	5

Academic Programs:	6

Context and Rationale	6

Strategic Planning Process	7

SECTION 2: SITUATIONAL ANALYSIS	8

SWOT Analysis	8

Stakeholder Analysis	9

Key Challenges Identified	9

SECTION 3: STRATEGIC DIRECTION	9

3.1 VISION	9

3.2 MISSION	9

3.3 CORE VALUES	10

3.4 Strategic Objectives	10

SECTION	4: STRATEGIC PRIORITIES & DETAILED ACTION PLANS	11

STRATEGIC PRIORITY 1: ENHANCE CBT/CBA QUALITY & IMPLEMENTATION	11

Goal 1.1: Achieve 100% adoption and effective implementation of CBT/CBA by 2028.	11

STRATEGIC	PRIORITY 2: STRENGTHEN INFRASTRUCTURE & LEARNING	13

RESOURCES	13

STRATEGIC PRIORITY3: DEVELOP	HUMAN CAPITAL & INSTITUTIONAL CAPACITY	14

Goal 3.1: Build highly competent workforce by 2030.	14

STRATEGIC PRIORITY 4: EXPAND INDUSTRY LINKAGES & PARTNERSHIPS	15

Goal 4.1: Establish strategic partnerships by 2028.	15

STRATEGIC	PRIORITY 5: ENHANCE STUDENT WELFARE & SUPPORT SERVICES	16

Goal 5.1: Comprehensive student support by 2027.	16

STRATEGIC	PRIORITY 6: STRENGTHEN GOVERNANCE&FINANCIAL MANAGEMENT	17

Goal 6.1: Transparent, efficient governance	17

SECTION 5: IMPLEMENTATION TIMELINES & MILESTONES	19

Five-Year Implementation Timeline (Gantt Chart Overview)	19

Year 1 (2026) Detailed Quarterly Milestones	19

Critical Milestones (2026-2030)	21

SECTION 6: MONITORING & EVALUATION FRAMEWORK	23

M&E Structure	23

Key Performance Indicators (KPIs)	23

Annual Review Template	24

Strategic Plan Scorecard	25

SECTION 7: DETAILED BUDGET BREAKDOWN	26

Five-Year Budget Summary	26

Year 1 (2026) Detailed Budget - Priority Highlights	27

Funding Sources (Projection)	28

SECTION 8: RISK MANAGEMENT FRAMEWORK	28

Risk Register	28

SECTION 9: SUSTAINABILITY STRATEGY	29

Financial Sustainability	29

Institutional Capacity Sustainability	29

SECTION 10: IMPLEMENTATION GOVERNANCE	29

Roles and Responsibilities	29

SECTION 11: STAKEHOLDER ENGAGEMENT	30

SECTION 12: COMMUNICATION STRATEGY	30

SECTION 13: ANNEXES	31

# EXECUTIVE SUMMARY

This five-year Strategic Plan (2026-2030) marks a transformative era for Bulinga Technical Secondary School (Bulinga TSS). Positioned in the Mushishiro Sector of Muhanga District.  Bulinga TSS aims to become a premier institution for ICT and Business education in the Southern Province. This plan articulates our roadmap to align with Rwanda's Education Sector Strategic Plan (ESSP) 2024-2029 and the National Strategy for Transformation (NST2), ensuring our graduates are equipped with market-relevant skills to drive the nation's digital economy.

## Key Strategic Priorities

To realize our vision of excellence, the school will focus on six interconnected strategic priorities:

- Enhance CBT/CBA Quality & Implementation: Improving instructional delivery and assessment integrity to meet NESA standards.

- Strengthen Infrastructure & Learning Resources: Modernizing workshops, labs, and digital access.

- Develop Human Capital & Institutional Capacity: Investing in staff pedagogical certification and leadership skills.

- Expand Industry Linkages & Partnerships: Bridging the gap between classroom theory and workplace reality.

- Enhance Student Welfare & Support Services: Fostering a holistic and supportive learning environment.

- Strengthen	Governance,	Leadership	&	Financial	Management:	Ensuring	accountability	and sustainability.

## Expected Outcomes by 2030

By the conclusion of this strategic period, Bulinga TSS envisions:

  - 100% of trainers certified in pedagogical skills by RTTI.

  - Full compliance with NESA quality standards, achieving a quality audit score above 80%.

  - Establishment of 4 fully operational smart classrooms and specialized software development labs.

  - A robust network of over 15 active industry partners providing internships and job placements.

  - A graduate employment rate exceeding 75% within six months of graduation.

### Resource Requirements

The successful implementation of this plan requires a total estimated investment of RWF 850,000,000 over five years. Funding will be sourced through government (60%), school fees (20%), development partners (10%), industry partnerships (5%), and internal revenue generation (5%).

# SECTION 1: INTRODUCTION & BACKGROUND

## About Bulinga TSS

Bulinga Technical Secondary School is a public TSS institution located in the Southern Province of Rwanda. Governed under the Ministry of Education (MINEDUC) and regulated by the Rwanda TVET Board (RTB) and National Examination and School Inspection Authority (NESA), the school serves as a critical hub for technical education in Muhanga District.

### Academic Programs:

    - Software Development (Levels 3, 4 & 5)

    - Network and internet technology (Level 3,4,5)

    - Computer system and architecture (Levels 3,4,5)

    - Accounting (Senior 4,5,6)

Currently, the school enrolls approximately 582 students and employs a dedicated staff of 32 trainers and support personnel 14. All programs are accredited; though continuous quality improvement remains a priority.

## Context and Rationale

The Government of Rwanda has prioritized TVET as a pillar for economic transformation. The ESSP 2024- 2029 emphasizes the need for quality, relevance, and inclusivity in education. However, the NESA Quality

Audit of 2023 highlighted specific gaps in public TSSs, including inconsistent implementation of Competency- Based Training and Assessment (CBT/CBA), insufficient resources, and gaps in internal verification systems.

This strategic plan is a direct response to those findings and national priorities. It serves as a directive framework to transition Bulinga TSS from a standard provider to a Center of Excellence.

## Strategic Planning Process

This document is the result of a participatory process involving:

    - Consultations: Workshops with staff, students, the School General Assembly Committee (SGAC), and local district officials.

    - Methodology: A comprehensive situational analysis using SWOT and PESTEL frameworks.

    - Validation: Draft review by the School Management Team and endorsement by the District Education Office.

# SECTION 2: SITUATIONAL ANALYSIS

## SWOT Analysis

| STRENGTHS | WEAKNESSES |
| --- | --- |
| - Public school status guarantees government support and salary payment. - Fully accredited programs in high-demand ICT and Business sectors. - Recent procurement of basic ICT equipment. - Strategic location accessible to students from Southern Province. - Established physical infrastructure (classrooms, admin block). | - Gaps in CBT/CBA process implementation and documentation. - Internal Verification systems are not fully systematic. - Less than 50% of trainers hold RTTI pedagogical certification. - Insufficient advanced learning resources (licensed software, specialized tools). - Weak formal partnerships with the private sector. - Inadequate e-library and digital research facilities. |
| OPPORTUNITIES | THREATS |
| - Rapidly growing demand for ICT skills in Rwanda's labor market. - Strong government prioritization and funding for TVET. - National digital transformation initiatives (Smart Rwanda). - Potential for partnerships with tech hubs in Kigali and Muhanga - RTB support programs for trainer development. - Rising trends in youth entrepreneurship and gig economy. | - Increasing competition from private TVET schools. - Rapid technological obsolescence requiring constant upgrades. - Brain drain of qualified ICT trainers to the private sector. - Limited discretionary funding for maintenance. - Stringent and evolving quality assurance requirements from NESA. |

## Stakeholder Analysis

    - Government (MINEDUC, RTB, NESA): Regulators and primary funders; key interest is compliance and quality.

    - Students & Parents: Beneficiaries; key interest is employability and value for education.

    - Staff: Implementers; key interest is professional growth and working conditions.

    - Industry Partners: Consumers of talent; key interest is skills relevance.

### Key Challenges Identified

    - Quality Assurance: Moving from theoretical teaching to true competency-based assessment.

    - Resource Constraints: Bridging the gap between budget allocations and the high cost of ICT infrastructure.

    - Capacity Development: Up-skilling trainers to keep pace with changing technology.

# SECTION 3: STRATEGIC DIRECTION

## 3.1 VISION

“To become a center of excellence in ICT and business education, producing competent, innovative graduates who drive Rwanda's digital economy and entrepreneurship by 2030.”

## 3.2 MISSION

“To provide quality, competency-based technical and vocational education that equips learners with relevant ICT, business, and soft skills for successful careers and sustainable socio-economic development.”

## 3.3 CORE VALUES

    - Excellence: Commitment to the highest standards in training and assessment.

    - Innovation: embracing creativity and new technologies.

    - Integrity: Upholding honesty and ethical conduct.

    - Inclusivity: Ensuring equal opportunity for all genders and abilities.

    - Industry-Responsiveness: Aligning curriculum delivery with market needs.

    - Teamwork: Collaborating for shared success.

## 3.4 Strategic Objectives

- Enhance CBT/CBA Quality & Implementation.

- Strengthen Infrastructure & Learning Resources.

- Develop Human Capital & Institutional Capacity.

- Expand Industry Linkages & Partnerships.

- Enhance Student Welfare & Support Services.

- Strengthen Governance, Leadership & Financial Management.

# SECTION	4: STRATEGIC	PRIORITIES	& DETAILED	ACTION PLANS

## STRATEGIC PRIORITY 1: ENHANCE CBT/CBA QUALITY & IMPLEMENTATION

### Goal 1.1: Achieve 100% adoption and effective implementation of CBT/CBA by 2028.

| Activity | Specific Actions | Responsible | Timeline | Resources | Expected Outputs | Indicators |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1.1 Establish Internal Verification System | - Form committee - Develop procedures - Train team | DOS, Academic Dept | 2026 Q1 | 500,000 RWF | Committee formed, procedures documented | Committee operational |
| 1.1.2 Conduct Termly Internal Verification | - Schedule activities - Review training plans - Verify assessments - Submit reports | Committee, HODs | 2026 Q2- Q4 (ongoing) | 800,000 RWF/term | Reports/year | 100% compliance |

| Activity | Specific Actions | Responsible | Timeline | Resources | Expected Outputs | Indicators |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1.3 Upgrade Trainer CBT Competencies | - Identify gaps - Enroll 50% in RTTI - Conduct workshops | Academic Dept | 2026 Q1- Q4 | 3,000,000 RWF | 50% certified by 2027 | Certification records |
| 1.1.4 Implement Trainee Portfolio System | - Develop e- portfolio platform - Train users - Monitor | ICT Dept, Academic Dept | 2026-2028/All Quarters | 6,000,000 RWF | System live | 95% student portfolios active |
| 1.1.5 Curriculum Contextualization | - Review trade specific modules - Adapt projects to local context | HODs | Weekly, Termly and Annual | Internal | Updated lesson plans | Approved training plans |

## STRATEGIC	PRIORITY	2:	STRENGTHEN	INFRASTRUCTURE	&	LEARNING

### RESOURCES

### Goal 2.1: Provide modern, adequate infrastructure supporting School partners.

| Activity | Specific Actions | Responsible | Timeline | Resources | Expected Outputs | Indicators |
| --- | --- | --- | --- | --- | --- | --- |
| 2.1.1 Develop | - Audit all | Finance, | 2026-2030 | 500,000 RWF | Complete | 100% |
| Comprehensive | equipment | HODs |  |  | inventory, | assets |
| Asset Inventory | - Create |  |  |  | Asset | tagged |
|  | database |  |  |  | register |  |
|  | - Tag assets |  |  |  |  |  |
| 2.1.2 Establish | - Assess needs | Maintenance | 2026 Q3 | 200,000 RWF | Maintenance | Plan |
| 5-Year | - Budget | Unit |  |  | plan | approved |
| Maintenance | allocations |  |  |  |  |  |
| Plan |  |  |  |  |  |  |
| 2.1.3 Upgrade | - Procure dev tools | ICT Dept, | 2026 | 6,000,000 RWF | Modern dev | Lab |
| Software Dev | - Install software | Procurement | Q2-Q4 |  | lab, 45 workstations | operational |
| Lab | - Network config |  |  |  |  |  |
| 2.1.4 Establish | - Building | Infrastructure, | 2026-2027 | 30,000,000 RWF | 3 smart | Used in |
| Smart | classrooms | ICT |  |  | classrooms | 80% |
| Classrooms | - Install |  |  |  |  | lessons |
| (Phase 1) | projectors/boards |  |  |  |  |  |
|  | - Network |  |  |  |  |  |
| 2.1.5 Library | - Procure e- | Librarian, ICT | 2027 Q3 | 5,000,000 RWF | E-library | Student |
| Digitalization | library software |  |  |  | portal | access |
|  | - Subscribe to Journals |  |  |  |  | Logs |

## STRATEGIC PRIORITY3: DEVELOP	HUMAN	CAPITAL	&	INSTITUTIONAL CAPACITY

### Goal 3.1: Build highly competent workforce by 2030.

| Activity | Specific Actions | Responsible | Timeline | Resources | Expected Outputs | Indicators |
| --- | --- | --- | --- | --- | --- | --- |
| 3.1.1 | - Identify | School | 2026 | 2,000,000 RWF | Full staff | Vacancy |
| Recruitment | staffing gaps | Management |  |  | complement | rate < 5% |
| Strategy | - Recruit |  |  |  |  |  |
|  | qualified |  |  |  |  |  |
|  | trainers |  |  |  |  |  |
| 3.1.2 | - Register | DSM, SM | Annual | See | 100% | Certificates |
| Pedagogical Certification | staff for RTTI - Monitor |  |  | Priority 1 | certified by 2030 |  |
|  | progress |  |  |  |  |  |
| 3.1.3 Technical Upskilling | - Industry attachments for trainers | DOS | Q4 Annual | 4,500,000 RWF/yr | Trainers upskilled | Industry certs obtained |

## STRATEGIC PRIORITY 4: EXPAND INDUSTRY LINKAGES & PARTNERSHIPS

### Goal 4.1: Establish strategic partnerships by 2030.

| Activity | Specific Actions | Responsible | Timeline | Resources | Expected Outputs | Indicators |
| --- | --- | --- | --- | --- | --- | --- |
| 4.1.1 Industry | - Identify partners | School Manager | 2026-2030 | 2,000,000 RWF | Committee formed | 4 meetings/ year |
| Advisory Committee | - Form committee - Quarterly meetings |  |  |  |  |  |
| 4.1.2 MOU Signing | - Approach 15 companies - Draft and sign MOUs | WPL | 2026- 2030 | 3,000,000 RWF | 15 MOUs Signed per year | Active MOUs |
| 4.1.3 Internship Program | - Placement of L5 students Supervision Field visit | DOS, HODs | Annual Q3 | 5,000,000 RWF | 100% placement | Internship reports |

## STRATEGIC	PRIORITY	5:	ENHANCE	STUDENT	WELFARE	&	SUPPORT SERVICES

### Goal 5.1: Comprehensive student support by 2027.

| Activity | Specific Actions | Responsible | Timeline | Resources | Expected Outputs | Indicators |
| --- | --- | --- | --- | --- | --- | --- |
| 5.1.1 Student Database | - Deploy management system - Data entry | Discipline, IT, DOS secretary | 2026-2030 | 3,000,000 RWF | Digital records | Database live |
| 5.1.2 Career Guidance Unit | - Appoint counselor - Setup office - Career fairs | DOS | 2026-2030 | 5,000,000 RWF | Functional unit | Student feedback |
| 5.1.3 Facility Improvements | - Renovate dining hall - Improve Kitchen building | Logistics | 2026 Q2-Q4 | 10,000,000 RWF | Improved welfare | Renovations complete |

## STRATEGIC	PRIORITY	6: STRENGTHEN	GOVERNANCE&FINANCIAL MANAGEMENT

### Goal 6.1: Transparent, efficient governance

| Activity | Specific Actions | Responsible | Timeline | Resources | Expected Outputs | Indicators |
| --- | --- | --- | --- | --- | --- | --- |
| 6.1.1 Policy | - Review | School | 2026 | 2,000,000 RWF | Updated | SOPs |
| Development | existing | Manager | Q1-Q2 |  | Policy | published |
|  | policies |  |  |  | Manual |  |
| 6.1.2 Financial System | - Install Accounting software - Train bursar | Bursar | 2026 | 200,000 RWF | Automated accounts | Clean audit Reports |
| 6.1.3 Communication | - Upgrade website Stakeholder meetings | IT, HOD, Head of trade Secretary | 2026/27 Q2-Q4 | 500,000 RWF | Active website | Engagement metrics |

# SECTION 5: IMPLEMENTATION TIMELINES & MILESTONES

## Five-Year Implementation Timeline (Gantt Chart Overview)

| Activity / Year | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| P1: CBT/CBA Quality | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Establish System |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
| Conduct Termly |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | X |
| Trainer Certification | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| P2: Infrastructure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lab Upgrades | x | x | x | x | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |
| Smart Classrooms | x | x | x | x | x | x | x | x |  |  |  |  | x | x | x | x |  |  |  |  |

## Year 1 (2026) Detailed Quarterly Milestones

Q1 (Jan-Mar 2026):

    - Internal Verification Committee established and tools developed.

    - Comprehensive asset inventory completed and database created.

    - Trainer skills gap analysis conducted.

    - Industry Advisory Committee formed.

    - Strategic Plan officially launched.

Q2 (Apr-Jun 2026):

    - First full Internal Verification cycle completed.

    - 5-Year Maintenance Plan developed.

    - 25% of trainers enrolled in RTTI certification.

    - 5 MOUs signed with industry partners.

    - Career Guidance Unit operational.

Q3 (Jul-Sep each fiscal year):

    - Software Development Lab hardware upgrade completed.

    - Leadership training for school management conducted.

    - Level 5 student internships commenced.

    - Mid-year performance review held.

Q4 (Oct-Dec 2026):

    - Third IV cycle completed; annual quality report drafted.

    - E-portfolio system pilot launched.

    - 50% of trainers achieve RTTI certification.

    - Alumni Association officially established.

## Critical Milestones (2026-2030)

| Year | Key Milestones | Target Date |
| --- | --- | --- |
| 2026 | IV system operational; Asset inventory complete; 50% trainers certified; 5 industry partners. | Dec 2026 |
| 2027 | 75% trainers certified; 2 smart classrooms; Internship program live; E-library launched. | Dec 2027 |
| 2028 | 90% trainers certified; 3 smart classrooms; 15 industry partners; NESA Quality score 75+. | Dec 2028 |
| 2029 | Full infrastructure upgrade; 75% graduate employment rate. | Dec 2029 |
| 2030 | 100% trainer certification; Center of Excellence status; NESA Quality score 80+. | Dec 2030 |

# SECTION 6: MONITORING & EVALUATION FRAMEWORK

## M&E Structure

    - Strategic Plan Implementation Committee (SPIC): Chaired by the Headmaster, meets monthly to track progress.

    - M&E Unit: Responsible for data collection and report generation.

## Key Performance Indicators (KPIs)

| KPI | Baseline End of 2025 | Target 2026 | Target 2028 | Target 2030 | Source |
| --- | --- | --- | --- | --- | --- |
| % of terms with reports | 0% | 100% | 100% | 100% | Academic Records |
| % Trainers RTTI Certified | 35% | 50% | 90% | 100% | File Records |
| NESA Audit Score | 57 | 62 | 73 | 78+ | NESA Report |
| Student Enrollment | 550 | 570 | 620 | 650 | Academic Records |
| Active Industry Partners | 2 | 5 | 15 | 20 | Partnership File |

BULINGA TSS - ANNUAL STRATEGIC PLAN REVIEW

Year: 	Date:

SECTION A: KPI PERFORMANCE

SECTION B: PRIORITY ASSESSMENT

Assess progress on 1-5 scale, achievements, challenges, and budget utilization.

BULINGA TSS - ANNUAL STRATEGIC PLAN REVIEW

Year: 	Date:

SECTION A: KPI PERFORMANCE

SECTION B: PRIORITY ASSESSMENT

Assess progress on 1-5 scale, achievements, challenges, and budget utilization.

Annual Review Template

| KPI | Target | Achieved | Status | Comments |
| --- | --- | --- | --- | --- |

## Strategic Plan Scorecard

| Perspective | Objective | Measure | Target |
| --- | --- | --- | --- |
| Quality | Deliver quality CBT | NESA Score | 75+ |
| Student | Graduate Competency | Pass Rate | 85% |
| Process | IV Compliance | IV Reports | 100% |
| Financial | Sustainability | Internal Revenue | +20% |

# SECTION 7: DETAILED BUDGET BREAKDOWN

### Five-Year Budget Summary

TOTAL STRATEGIC PLAN BUDGET: RWF 850,000,000 (2026-2030)

| Strategic Priority | Total Budget | % | 2026 | 2027 | 2028-2030 |
| --- | --- | --- | --- | --- | --- |
| 1. CBT/CBA Quality | 120,000,000 | 14% | 35,000,000 | 30,000,000 | 55,000,000 |
| 2. Infrastructure & Resources | 380,000,000 | 45% | 100,000,000 | 120,000,000 | 160,000,000 |
| 3. Human Capital | 150,000,000 | 18% | 35,000,000 | 40,000,000 | 75,000,000 |
| 4. Industry Linkages | 50,000,000 | 6% | 12,000,000 | 15,000,000 | 23,000,000 |
| 5. Student Welfare | 80,000,000 | 9% | 20,000,000 | 25,000,000 | 35,000,000 |
| 6. Governance | 40,000,000 | 5% | 10,000,000 | 12,000,000 | 18,000,000 |
| Contingency & M&E | 30,000,000 | 3% | 8,000,000 | 8,000,000 | 14,000,000 |
| TOTAL | 850,000,000 | 100% | 220,000,000 | 250,000,000 | 380,000,000 |

### Year 1 (2026) Detailed Budget - Priority Highlights

| Activity | Item | Cost (RWF) | Period |
| --- | --- | --- | --- |
| Priority 1: CBT/CBA Quality (35,000,000 Total) |  |  |  |
| Internal Verification | Training & Tools | 3,000,000 | Q1 |
| Trainer Certification | RTTI Fees (15 staff) | 25,000,000 | Q1-Q4 |
| E-Portfolio | Platform Dev | 7,000,000 | Q3 |
| Priority 2: Infrastructure (100,000,000 Total) |  |  |  |
| Lab Upgrade | Workstations & Server | 60,000,000 | Q2 |
| Comp App Lab | PCs & Software | 25,000,000 | Q3 |
| Asset Management | Software & Tagging | 3,000,000 | Q1 |

### Funding Sources (Projection)

    - Government Budget: 60% (510,000,000 RWF)

    - School Fees: 20% (170,000,000 RWF)

    - Development Partners: 10% (85,000,000 RWF)

    - Industry & Internal Revenue: 10% (85,000,000 RWF)

# SECTION 8: RISK MANAGEMENT FRAMEWORK

## Risk Register

| Risk | Cat | Prob | Impact | Level | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- |
| Insufficient infrastructure funding | Fin | 4 | 5 | CRITICAL | Early budget submission; Diversify funding; Phased implementation. |
| Trainer turnover to private sector | RTB | 3 | 4 | HIGH | Competitive packages; Professional development; Recognition. |
| Equipment obsolescence | Tech | 4 | 3 | HIGH | Annual tech refresh; Leasing options; Industry partnerships. |
| NESA quality non- compliance | Reg | 3 | 5 | CRITICAL | Robust IV system; Regular mock audits; Staff training. |

# SECTION 9: SUSTAINABILITY STRATEGY

## Financial Sustainability

To reduce reliance on government capitation, Bulinga TSS will pursue:

    - Short Courses: Offering weekend/evening classes in Python, Web Development, and Accounting packages for the community.

    - ICT Services: A student-led production unit offering computer repair and basic IT services.

    - Consultancy: Leveraging trainer expertise for local business support.

## Institutional Capacity Sustainability

We will build a culture of excellence where quality assurance is embedded in daily operations, ensuring that high standards survive staff turnover through robust SOPs and knowledge management systems.

# SECTION 10: IMPLEMENTATION GOVERNANCE

## Roles and Responsibilities

| Entity | Role |
| --- | --- |
| School General Assembly (SGAC) | Strategic oversight, policy approval, and resource mobilization. |
| Headmaster | Overall leadership, accountability officer, external relations. |
| Strategic Plan Committee (SPIC) | Coordination of implementation, progress monitoring, problem-solving. |
| Technical Working Groups | Execution of specific priority areas (e.g., Infrastructure Group, Academic Group). |

# SECTION 11: STAKEHOLDER ENGAGEMENT

Effective implementation requires active engagement with:

    - MINEDUC/RTB/NESA: Quarterly reporting to ensure regulatory alignment.

    - Industry Partners: Bi-annual advisory meetings to review curriculum relevance.

    - Parents & Students: Termly meetings to ensure satisfaction and support.

# SECTION 12: COMMUNICATION STRATEGY

Internal: Weekly staff briefings, notice boards, digital platforms (intranet).

External: An upgraded school website, annual reports published online, and community open days to showcase student innovations.

# SECTION 13: ANNEXES

###### Annex A: Detailed Activity Implementation Plans

(Refer to full separate planning documents)

###### Annex B: Policy Documents

- Internal Verification Policy

- Asset Management Policy

- Student Welfare Policy

###### Annex C: Key Reference Documents

- Rwanda ESSP 2024-2029

- RTB Strategic Plan 2021-2024

- NESA Quality Standards

Bulinga Technical Secondary School	Strategic Plan 2026-2030	Page End